## Section 1 & 2
1. DOCUMENT IDENTIFICATION
Document Identification
| Project Name | RILey |  | Project No. | RILey001
| Version | 1 |  | Date | 2022-05-16
|  | Name |  | Signature |  | Date
| Author | Alexandru Pășescu |  |  |  | 2022-05-16
| Author | Quinvey Etienne |  |  |  | 2022-05-16
| Author | Martijn Strolenberg |  |  |  | 2022-05-16
| Author | Niels van Hinsberg |  |  |  | 2022-05-16
| Author | Toby van Dueren den Hollander |  |  |  | 2022-05-16
| Reviewed by | Reviewer |  | X |  | xx-xx-xxxx
| Revision | Description |  | Changed by |  | Date
| A | Initial Draft |  | All |  | 2022-05-16
2.1 PROJECT INFORMATION
MACHINE INFORMATION
| Machine Name: |  | RILey Robot
| Manufacturer: |  | Team RILey
| Machine Type: |  | Reconnaissance Robot
| Serial Number: |  | 1
| Date of Manufacture: |  | 2022-05-09
| Machine Certification: |  | N/a
DEVICE INFORMATION
| Device Name: |  | RILey Robot
| Manufacturer: |  | Team RILey
| Device Type: |  | Reconnaissance Robot
| Serial Number: |  | 1
| Date of Manufacture: |  | 2022-05-09
| Device Certification: |  | N/a
ASSESSMENT PERSONNEL / ASSESSMENT DATE
Initial Risk Assessment
| Author: |  | Alexandru Pășescu |  | Date: | 2022-05-16
| Author: |  | Quinvey Etienne |  | Date: | 2022-05-16
| Author: |  | Martijn Strolenberg |  | Date: | 2022-05-16
| Author: |  | Niels van Hinsberg |  | Date: | 2022-05-16
| Author: |  | Toby van Dueren den Hollander |  | Date: | 2022-05-16
CUSTOMER PERSONNEL
| Name: | Sjriek Alers |  | Function/ Job Title: |  | Lecturer, Client
| Name: | Danny Hameeteman |  | Function/ Job Title: |  | Engineer, Project holder
2.2 MOTIVATION
This document is a risk assessment example for collaborative robots users. This is based on a Pilz© documentation format to conduct a formal risk assessment on the RILey Robot.
This risk assessment complies with the [enumerate applicable standards].
The construction, safeguarding, and risk sources were evaluated for compliance with applicable standards listed in this report.
This Risk Assessment has been carried out Using the Pilz methodology on 16 May 2022. Pilz does not take responsibility for the contents of this Risk assessment
2.3 METHOD OF RISK ANALYSIS
In accordance with ISO 12100, the risk assessment is implemented in a series of logical steps to enable a systematic examination of the hazards associated with machinery. Risk assessment is followed, whenever necessary by risk reduction as described in clause 6 of ISO 12100: 2010. When this process is repeated it gives an iterative process for eliminating hazards as far as possible and for implementing safety measures.
The risk assessment methodology approach includes: -- Risk analysis o Determination of limits o Hazard identification o Risk estimation -- Risk evaluation
The risk assessment provides the information required for the risk evaluation, which in turn allows judgements to be made on the safety of machinery.
The Diagram 1 shows the step-by-step process of risk analysis:
Diagram 1: Method of risk reduction
2.4 LIMIT OF REPORT
This risk assessment report is based on information that was accumulated during the on-site risk assessment of the RILey Robot at Fontys University of Applied Sciences on the 16-05-2022.
This risk assessment for work equipment examines significant hazards where risk reduction measures still need to be applied.
The information was accumulated in the following fashion: 1. Reviewing all available machine technical information 2. Conducting a physical examination of the machine
In order to ensure the accuracy of the risk assessment for the machine, it is imperative that the information provided on the date of the risk assessment be correct and reliable. Team RILey cannot take any responsibility for judgements made on inaccurate or lack of information.
Every effort is made to evaluate the risk associated with each hazard identified throughout the report, however it may not be possible to quantify the risk with all hazards. When this is not possible the hazards are assessed in relation to their conformance with all relevant Legislation. Each hazard is identified individually throughout the report; the outcome from the accumulation of hazards has not been evaluated.
Human error and misuse related to areas such as incorrect feeding of the machine, incorrect use of materials and operator ability to operate the machine are not considered to be under the scope of this report. Only clear foreseen misuse of the machine was considered.
Due to practical reasons not all the machine lifecycle was examined as part of this report, the following phases were excluded: - Assembly Installation - Decommissioning - Disposal - Transport - Construction - Commissioning

## Section 3
3. MACHINE ASSESSMENT
3.1 BASIC MACHINE DESCRIPTION
The RILey robot is used as an autonomous reconnaissance platform for scanning (un)known locations suchs as buildings. This scanning task is performed by combining sensory data, and sending this to a remote server where this data can be processed and interpreted. The platform is powered by two motors which are connected to large wheels which also provide the damping of the platform.
Visualising the surroundings is accomplished by using a camera feed in combination with LIDAR and Time of flight sensor. The operator must be able to end the autonomous operation at any time, and resume operation via manual commands.
Because the platform is power by Li-ion battery packs, the operating time is around 1 hour.
[place photo here]
Picture 1: Robotic cell used for risk assessment example
3.2 MACHINE CONTROL SYSTEM DESCRIPTION
The RILey robot is controlled by a Raspberry Pi model 4B. This controller controls the two stepper motors.
3.3 MACHINE SPECIFICATION
MACHINE LIMITS
| Machine Name/Type |  | RILey Robot
| Intended Environment: |  | Indoor
| Required Training Level: |  | Basic Training
| Operated by: |  | Operator, Maintenance Technician
| Intended Use: |  | (Autonomous) Reconnaissance
| Machine Lifetime: |  | 6 - 12 months
| Machine Dimensions: |  | 230mm x 253mm x 155 mm
| Machine Environment: |  | dry, clean, non explosive, non flammable.
OPERATIONAL AND MAINTENANCE INFORMATION
Operational Information
| Emergency Stopping Time: |  | << 1 sec
| Machine Cycle Time: |  | << 1 m/s
| No. of Operators: |  | 1 in normal use
Maintenance Information
| Maintened by: |  | Team RILey
| Maintenance Frequency: |  | Not required
| Cleaning: |  | No cleaning required
| Jamming Repair: |  | Team RILey
POWER SOURCES
| Control, Elec. Supply: |  | 2x 12V DC LI-ION battery pack
3.4 RISK ESTIMATION & EVALUATION CRITERIA
The Evaluation methodology is based on Pilz criteria and experience, an evaluation of the factors, Degree of Possible Harm (DPH), Probability of Occurrence of a Hazardous Event (PO), Possibility of Avoidance (PA) and Frequency and/or duration of Exposure (FE), and has been performed on the risk related with each hazard. A Pilz Hazard Rating has then been calculated from the following formula:
PHR = DPH x PO x PA x FE
Where the above parameters can take the following values:
Degree of Possible Harm (DPH) 0.25 Scratch / Bruise 0.5 Laceration / cut / mild ill health effect/ minor burns 3 Fracture minor bone – fingers, toes 5 Fracture major bone – hand, arm, leg 8 Loss of 1 or 2 fingers/ toes or major burns 11 Leg / hand amputation, partial loss of hearing or eye 15 Amputation of 2 legs/hands, total loss of hearing/sight in both ears/eyes 25 Critical injuries or permanent illness/condition/injury 40 Single Fatality 65 Catastrophe
Possibility of Occurrence of Hazard Event (PO) 0.05 Almost impossible 1.25 Unlikely 2.5 Possible 4 Probable 6 Certain
Possibility of Avoidance (PA) 0.75 Possible 2.5 Possible under certain circumstances 5 Not Possible
Frequency of Exposure (FE) 0.5 Annually 1 Monthly 2 Weekly 3 Daily 4 Hourly 5 Constantly
The maximum and minimum numerical values that could be assigned to each factor for every hazard are shown in the following table.
| PHR |  | Risk |  | Comment
|  | 1-10 | Negligible Risk |  | Presents practically no risk to health and safety, no further risk reduction measures are required.
|  | 11-20 | Very Low Risk |  | Presents very little risk to health and safety, no significant risk reduction measures are required, may necessitate the use of personal protective equipment and/or training.
|  | 21-45 | Low Risk |  | Risk to health and safety is present, but low. Risk reduction measures must be considered.
|  | 46-160 | Significant Risk |  | The risk associated with the hazard is substantial enough to require risk reduction measures. These measures should be implemented at the next suitable opportunity.
|  | 161-500 | High Risk |  | Potentially dangerous hazard, which requires risk reduction measures to be implemented urgently.
|  | 501+ | Very high Risk |  | Risk reduction measures should be implemented immediately, corporate management should be notified.
Table X: PHR Numeric Range
After a complete examination of the machine based on applicable standards, a numerical value was determined for each factor while conducting the Risk Assessment and the Pilz Hazard Rating was calculated. The calculated number was then used to evaluate the risk associated with the hazard by comparison with predetermined acceptable levels.
The calculated Pilz Hazard Rating ranges from 1 to 9750 where 1 is the lowest showing minimum and 9750 is the highest risk.
3.5 Findings
| Hazard Identification | [5 empty] | Hazard No. | 1.1
| Title | Falling Hazard
| Location | Everywhere
| Target | Head, shoulders, arms and feet
| Activity | Normal operation
| Task | Driving
| Sub Task | Both Autonomous and Manual driving
| Hazard Type | Mechanical Hazard with the consequence of collision
| Sub Type | Crushing and impact (Quasi-static)
Description
References:
Risk Estimation and Evaluation
| Degree of Possible Harm: |  |  | 25 | Possibility of Avoidance: |  |  | 0.75
| Probability of Occurance of a Hazardous Event: |  |  | 2 | Frequency And/or Duration of Exposure: |  |  | 5
| Pilz Hazard Rating (PHR): |  |  | 187.5 | Summary Level: |  | High Risk
| Risk Reduction | [5 empty] | Reference
Nessecery, add a time of flight sensor so it can detect a cliff and will stop before it falls off.
Risk Estimation and Evaluation
| Degree of Possible Harm: |  |  | 25 | Possibility of Avoidance: |  |  | 0.75
| Probability of Occurance of a Hazardous Event: |  |  | 0.05 | Frequency And/or Duration of Exposure: |  |  | 0.5
| Pilz Hazard Rating (PHR): |  |  | 0.46875 | Summary Level: |  | Negligible Risk
| Hazard Identification | [5 empty] | Hazard No. | 1.2
| Title | Tripping
| Location | Everywhere
| Target | Entire body
| Activity | Normal operation
| Task | Driving
| Sub Task | Both Autonomous and Manual driving
Sub task
| Hazard Type | Mechanical Hazard with the consequence of physical damage
| Sub Type | Crushing and impact (Quasi-static)
| Description | A person can trip over the robot. This can result in physical damage to the robot and the person.
References:
Risk Estimation and Evaluation
| Degree of Possible Harm: |  |  | 25 | Possibility of Avoidance: |  |  | 0.75
| Probability of Occurance of a Hazardous Event: |  |  | 4 | Frequency And/or Duration of Exposure: |  |  | 1
| Pilz Hazard Rating (PHR): |  |  | 75 | Summary Level: |  | Significant Risk
| Risk Reduction | [5 empty] | Reference
The robot has a Time of Flight sensor and a Lidar witch can sense if a object is infront of the robot. It will stop or drive around the detected object / person.
Risk Estimation and Evaluation
| Degree of Possible Harm: |  |  | 25 | Possibility of Avoidance: |  |  | 2.5
| Probability of Occurance of a Hazardous Event: |  |  | 0.05 | Frequency And/or Duration of Exposure: |  |  | 0.5
| Pilz Hazard Rating (PHR): |  |  | 1.5625 | Summary Level: |  | Negligible Risk
| Hazard Identification | [5 empty] | Hazard No. | 1.3
| Title | Fire Hazard
| Location | Everywhere
| Target | Entire body
| Activity | Normal operation
| Task | Driving
| Sub Task | Both when charging and on idle state
| Hazard Type | Burning
| Sub Type | /
| Description | Damaged batteries can cause the robot to catch fire during operation or charging.
References:
Risk Estimation and Evaluation
| Degree of Possible Harm: |  |  | 1 | Possibility of Avoidance: |  |  | 0.75
| Probability of Occurance of a Hazardous Event: |  |  | 1.25 | Frequency And/or Duration of Exposure: |  |  | 3
| Pilz Hazard Rating (PHR): |  |  | 2.8125 | Summary Level: |  | Negligible Risk
| Risk Reduction | [5 empty] | Reference
the Batteries have a battery management system (BMS) that will make sure the batteries wont overcharge or undercharge. Also it is protected against shorts. The motor heat can be solved by using more advanced stepper drivers so the motors use less current for the same motion. That way they also be a lot cooler.
Risk Estimation and Evaluation
| Degree of Possible Harm: |  |  | 1 | Possibility of Avoidance: |  |  | 0.75
| Probability of Occurance of a Hazardous Event: |  |  | 1.25 | Frequency And/or Duration of Exposure: |  |  | 0.5
| Pilz Hazard Rating (PHR): |  |  | 0.46875 | Summary Level: |  | Negligible Risk
| Hazard Identification | [5 empty] | Hazard No. | 1.4
| Title | Burning Hazard
| Location | Everywhere
| Target | Arms and feet
| Activity | Touching or picking up the RILey
| Task | Being on
| Sub Task | On idle state, or when moving a lot
| Hazard Type | Burning skin
| Sub Type | /
| Description | The heat of the motors can be arround 70 to 85 degrees that will be sufficient to small degree of burning skin upon contact.
References:
Risk Estimation and Evaluation
| Degree of Possible Harm: |  |  | 1 | Possibility of Avoidance: |  |  | 0.75
| Probability of Occurance of a Hazardous Event: |  |  | 2.5 | Frequency And/or Duration of Exposure: |  |  | 4
| Pilz Hazard Rating (PHR): |  |  | 7.5 | Summary Level: |  | Negligible Risk
| Risk Reduction | [5 empty] | Reference
Risk Estimation and Evaluation
| Degree of Possible Harm: |  |  | 1 | Possibility of Avoidance: |  |  | 0.75
| Probability of Occurance of a Hazardous Event: |  |  | 2.5 | Frequency And/or Duration of Exposure: |  |  | 4
| Pilz Hazard Rating (PHR): |  |  | 7.5 | Summary Level: |  | Negligible Risk
| Hazard Identification | [5 empty] | Hazard No. | 1.5
| Title | Crushing Hazard
| Location | Everywhere
| Target | Feet
| Activity | Normal operation
| Task | Driving
| Sub Task | Both autonomous and manual operation
| Hazard Type | Scratched skin
| Sub Type | /
| Description | The sheer mass, sharp edges and destructive speed the RILey can accieve.
References:
Risk Estimation and Evaluation
| Degree of Possible Harm: |  |  | 0.25 | Possibility of Avoidance: |  |  | 0.75
| Probability of Occurance of a Hazardous Event: |  |  | 2.5 | Frequency And/or Duration of Exposure: |  |  | 2
| Pilz Hazard Rating (PHR): |  |  | 0.9375 | Summary Level: |  | Negligible Risk
| Risk Reduction | [5 empty] | Reference
Risk Estimation and Evaluation
| Degree of Possible Harm: |  |  | 0.25 | Possibility of Avoidance: |  |  | 0.75
| Probability of Occurance of a Hazardous Event: |  |  | 2.5 | Frequency And/or Duration of Exposure: |  |  | 2
| Pilz Hazard Rating (PHR): |  |  | 0.9375 | Summary Level: |  | Negligible Risk
3.6 Priority Listing
| Priority | Hazard No. | Hazard Name |  | PHR | Risk Level
| 1 | 1.1 | Falling Hazard |  | 187.5 | High Risk
| 2 | 1.2 | Tripping |  | 75 | Significant Risk
| 3 | 1.4 | Burning Hazard |  | 7.5 | Negligible Risk
| 4 | 1.3 | Fire Hazard |  | 2.8125 | Negligible Risk
| 5 | 1.5 | Crushing Hazard |  | 0.9375 | Negligible Risk
3.7 Risk Reduction
Due to the hazards detailed in the earlier section 3.6 Findings, it is necessary to carry out a risk reduction for each hazard where the estimated risk is determined to be unacceptable as detailed in the findings.
After the required safety measures are implemented it will be necessary to ensure that the risk posed by each hazard has been reduced to the level specified in this document by performing a final risk evaluation.
On completion of the risk reduction measures and the final risk evaluation, the residual risk associated with all hazards will have to be assessed and documented as part of the risk assessment report. This is the possible risk that a hazard may possess even after risk reduction measures have been implemented due to the fact that it was not possible to design a complete safety solution to eradicate the risk.
In order to inform the user of these residual risks related with the machine that have not been reduced by the design of contra measures, special indications should be included in the operator procedure documentation and warnings should be placed on the machine.
4 Conclusion
Overall, when the Riley robot is operational it forms a verly low risk for people and its surrounding. When its in operation mode it can attain the risk level required for compliance to the ISO/TS 15066, however some of the risk sources listed in section 3.5 and 3.6 requires further risk reduction.
Eindhoven,
16th of May 2022
zw = m*g*h
𝐸zw = m*g*h
𝐸𝑘=1/2∗𝑚∗𝑣^2
8,9 m/s
𝑣= 8,9 m/s
The falling speed of the robot with a starting height of 4m is around 8.9 m/s.

## Appendix 1
Appendix 1 : Terminology
| Machinery / Machine: | Assembly, fitted with or intended to be fitted with a drive system consisting of linked parts or components, at least one of which moves, and which are joined together for a specific application.
| Reliability: | The ability of a machine or components, or equipment to perform a required function under specified conditions and for a given period of time without failing.
| Safety of machine: | The ability of a machine to perform its function, to be transported, installed, adjusted, maintained, dismantled and disposed of under conditions of intended use specified in the instruction handbook without causing injury or damage to health.
| Hazard: | A potential source of harm.
| Hazardous situation: | Any situation in which a person is exposed to a hazard or to hazards.
| Risk: | A combination of the probability of occurrence of harm and the severity of that harm.
| Risk Assessment: | Overall process comprising a risk analysis and a risk evaluation.
| Harm: | Physical injury or damage to health.
| Danger zone (or Hazard zone): | Any space within and/or around machinery in which a person can be exposed to a hazard.
| Exposed person: | Any person wholly or partially in a danger zone.
| Operator: | The person or persons given the task of mainly operating machinery. Minor adjusting, maintaining, and cleaning tasks might also be executed.
| Preliminary Hazard Analysis: | PHA is an inductive method, whose objective is to identify, for all phases of life of a specified system / subsystem / component the hazards, hazardous situations and hazardous events which could lead to an accident.
| Performance Level: | Discrete Level used to specify the ability of the safety-related parts of a control system to perform a safety function under unforeseeable conditions
| Safety Component: | A component placed on the market separately to fulfil a safety function when in use and the failure or malfunctioning of which endangers the safety or health of exposed persons
| Warning devices: | Visible/audible alarms to trigger avoidance or corrective responses (e.g., signals, lights, signs, horns). Training and discipline in recognizing and responding is necessary. Their value to personnel with vision or hearing impairments is questionable.
| Procedures and training: | Formal or informal training, checklists, certification or experience requirements, personal protective equipment use.
| Residual risk: | Risk remaining after protective measures have been implemented.
| Safeguarding: | Protective measure using safeguards to protect persons from the hazards which cannot reasonably be eliminated or from the risks which cannot be sufficiently reduced by inherently safe design measures
| Safety function: | Function of a machine whose failure can result in an immediate increase of the risk(s)
| Failure: | The termination of the ability of an item to perform a required function.
| Emergency situation: | Hazardous situation needing to be urgently ended or averted.
| Machine control system: | System which responds to an input from, for example, the process, other machine elements, an operator, external control equipment, and generates an output(s) causing the machine to behave in the intended manner.
| Safety-related electrical control system (SRECS): | Electrical, electronic or programmable electronic part of a machine control system whose failure can result in an immediate increase of the risk(s)
| Safety Related Part of a Control System (SRP/CS): | Part of a control system that responds to safety-related input signals and generates safety-related output signals
| Diagnostic function: | Function intended to detect faults in the control system and produce a specified output information or activity when a fault is detected.
| Safety Integrity: | Probability of a Safety Related Electrical Control System or its subsystem satisfactorily performing the required safety functions under all stated conditions
| Task: | Specific activity performed by one or more persons on, or in the vicinity of, the machine during its life cycle.
| Reasonably foreseeable misuse: | Use of a machine in a way not intended by the designer, but which can result from readily predictable human behaviour.
| Safety of control systems: | Ability of safety-related parts of a control system to perform their safety function(s) for a given time according to their specified category or performance level
| Hazardous machine function: | Any function of a machine, which generates a hazard when operating.
| Risk reduction, adequate: | Risk reduction at least in accordance with the legal requirements under consideration of the current state of the art.
| Protective Measure: | Measure intended to achieve risk reduction.
| Inherently Safe Design Measure: | Protective measure which either eliminates hazards or reduces the risks associated with hazards by changing the design or operating characteristics of the machine without the use of guards or protective devices.
| Hazard, relevant: | Hazard which is identified (as part of the risk assessment process) as being present at, or associated with the machine.
| Hazard, significant: | Hazard which has been identified as relevant and which requires specific action to eliminate or to reduce the risk according to the risk assessment.
| Hazardous event: | Event that can cause harm. A hazardous event can occur over a short period of time or over an extended period of time.
| Inherently safe design measures: | Protective measure which either eliminates hazards or reduces the risks associated with hazards by changing the design or operating characteristics of the machine without the use of guards or protective devices.
| Information for use: | Protective measure consisting of communication links (for example, text, words, signs, signals,symbols, diagrams) used separately or in combination, to convey information to the user.
| Intended use: | Use of a machine in accordance with the information for use provided in the instructions.
| Risk analysis: | Combination of the specification of the limits of the machine, hazard identification and risk estimation.
| Risk estimation: | Defining likely severity of harm and probability of occurrence.
| Risk evaluation: | Judgement, on the basis of risk analysis, of whether the risk reduction objectives have been achieved.

## Appendix 2
Appendix 2 : Abbreviations
Not Accept: Not Acceptable
BPCS: Basic Process Control System
SRS: Safety Requirement Specification
FDS: Functional Design Specification
HAZOP: Hazard and Operability Study
EMC: Electromagnetic Compatibility
CCF: Common Cause Failure
PFD: The Probability of Failure on Demand
MTBF: Mean Time Between Failures
MTTF: Mean Time To Failure
MTTR: Mean Time To Restoration
PHA: Preliminary Hazard Analysis
PL: Performance Level
SIF: Safety Instrumented Function
SIL: Safety Integrity Level
SIS: Safety Instrumented System
SFF: Safe Failure Fraction
DC: Diagnostic Coverage
I/O: Input/Output
FB: Function Block
PFHD: Probability of dangerous Failure per Hour
SRCF: Safety-Related Control Function
SYS: System
URS: User Requirement Specification
SRP/CS: Safety-related part of a control system
SRECS: Safety-related electrical control system
APM Alternative protective measure, a protective measures using protective
devices in a circuit of adequate integrity level as determined by a risk
assessment to provide effective protection of personnel during minor servicing
in place of an energy isolation lockout.